## Sheet1
Step # | Depends On Step # | Task |  | Assigned To | Target Date | Date Completed
1 |  | PLANNING
Meet with Troop Committee to establish goals, responsibilities and schedule
Determine best sources of data for membership, advancement, participation, leadership, training & account balances
Decide whether to allow scouts to request sign off on requirements through the website and app
Decide whether the site will accept credit card payments and, if so, who will pay the credit card fees
Decide whether to allow adults to request expense reimbursements through the website
If you have both a girl troop and boy troop, decide whether to share one site or have separate sites (possibly linked)
Fill out this checklist and send to all committee members
2 | 1 | INITIAL ROSTER
A) If a data source exists, upload membership data for all scouts and adults
B) Otherwise, enter membership data for adult leaders who will be helping set up the site
3 | 2 | SECURITY
Assign additional user roles to user IDs of adult leaders
Send user IDs and passwords to leaders who are helping set up the site
4 | 3 | ROSTER
If not possible to upload membership data, manually enter membership records for everyone else using New Scout Registration page
Set up patrols and update patrol membership
Upload or enter current scout leaders
Enter current adult leaders
Upload or enter adult training
Create dynamic subgroups
Ask all adult leaders to enter their "About Me" section and upload a photo under My Contact Information
5 | 3 | PUBLIC PAGES
Create banner image (optional)
Edit the Home page and About Our Troop pages
Create additional custom pages as needed
Create announcements
Upload troop forms and documents
Create resource links
6 | 3 | CALENDAR
Customize event types as needed
Enter event locations
Enter past events for which you plan to upload photos or enter monetary transactions
Enter upcoming events. Use the "copy event" functions to set up meetings and other recurring events
Train leaders to use mobile app to take attendance at events.
7 | 6 | PHOTO GALLERY / VIDEO GALLERY
Upload photos from past events
Upload videos to YouTube and create links from Video Gallery
8 | 4 | ADVANCEMENT
A) If a data source exists, upload advancement data for all scouts
B) Otherwise, enter advancement data for all scouts
Upload or enter participation history for past camping nights, service hours, hiking miles, etc.
Review and update advancement settings
Enter merit badge counselor assignments
Train adult leaders how to sign off on requirements on the website and the app
9 | 3 | INVENTORY/LIBRARY
Enter all library materials into troop inventory
Enter all troop equipment into troop inventory
Check out items to troop members who currently have them
Train leaders to use mobile app to check out and return library materials and troop equipment
10 | 4 | ACCOUNTING
Set up troop accounts and enter starting balances
Set up personal subaccounts for reserve accounts and fundraising proceeds
A) If data source is available, upload Adult and Scout balances
B) Otherwise, enter starting balances for each troop member
Set up credit card interface using Square or PayPal
Review and update expense reimbursement settings
Train leaders to use website to request expense reimbursements
Begin monthly statement reconciliation process
11 | 4 | FUNDRAISERS
Set up sales campaign for next fundraiser, including merchandise and sales prizes
Train scouts how to enter orders and sell on-line via ScoutSales.org
Train fundraising leaders how to use Booth Sales to run in-person fundraiser events
12 | 4 | TROOP MERCHANDISE
Set up sales campaign for sales of troop merchandise, like troop t-shirts
Train scouts and adults how to "buy stuff from troop"
13 | 4 | ROLL OUT
Send user ID's and passwords to all troop members
Demonstrate/discuss new website and mobile app at troop meetings
Train scouts and parents to use mobile app to sign up for events and give permission
Train scouts to use mobile app to request sign off on requirements
Plan on-going site operation at committee meeting